## Tasks
Task | Employee | Project | Status | Priority | Due Date
Admin Permissions Auto-Update Fix | Mohammad Ziya | One Humanity Portal | Pending | Low | 2025-12-31
Admin Dashboard Tooltip Implementation | Mohammad Ziya | One Humanity Portal | To Do | Medium | 2025-12-27
HR Dashboard | Sahid ansari | One Humanity Portal | To Do | Medium | 2025-12-26
Admin Dashboard Optimization & Freeze | Mohammad Ziya | One Humanity Portal | Pending | Low | 2025-12-31
Employee Dashboard UI Polish | Mohammad Ziya | One Humanity Portal | To Do | Medium | 2025-12-31
Project Centralization & Workflow Alignment | Om Vashishtha | One Humanity Portal | Completed | High | 2025-12-24
Admin Permissions Auto-Update Fix | Mohammad Ziya | One Humanity Portal | Completed | High | 2025-12-24
Manager Dashboard - Core Developement | Aishwarya Gupta | One Humanity Portal | To Do | Medium | 2025-12-25